## Release Plan
Increment Plan
Incr. | Start | Days | End | Estimated Size | Real Size | Status | Release Date | Goal | % Esfuerzo vs Estimación
1 | 2022-10-12 | 3 | 2022-10-14 | 6.122% | 6.122% | Released | 2022-10-12 | Entrega Sprint 0 (Conformacion de equipo / Idea / Roles) | 100%
1 | 2022-10-12 | 12 | 2022-10-23 | 24.49% | 24.49% | Released | 23/10/200 | Entrega Sprint 1 (Documentacion Preliminar/repositorios/alcance) | 100%
Unplanned
Unplanned
Unplanned
Unplanned
Sprint Plan
Sprint | Start | Days | End | Estimated Size | Real Size | Status | Release Date | Goal | Increment | % Error estimación
0 | 2022-10-10 | 1 | 2022-10-10 | 1 | 1 | Released | 2022-10-10 | Construccion Incial de MockUps | 1 | 0%
0 | 2022-10-11 | 1 | 2022-10-11 | 1 | 1 | Released | 2022-10-11 | Construccion Inicial de Diagrama UML | 1 | 0%
0 | 2022-10-12 | 1 | 2022-10-12 | 1 | 1 | Released | 2022-10-12 | Diligenciamiento de documento IEEE 29148 | 1 | 0%
1 | 2022-10-12 | 1 | 2022-10-12 | 2 | 2 | Released | 2022-10-12 | Desarrollar Product Backlook Priorizado | 1 | 0%
1 | 2022-10-13 | 2 | 2022-10-14 | 1 | 1 | Released | 2022-10-14 | Construir Repositorio (Github) donde integraran el Trabajo | 1 | 0%
1 | 2022-10-15 | 2 | 2022-10-16 | 2 | 2 | Released | 2022-10-16 | Construir Archivo Gestion Configuracion | 1 | 0%
1 | 2022-10-17 | 5 | 2022-10-21 | 5 | 5 | Released | 2022-10-21 | Construir Historias de Usuario a desarrollar en Sprint No.1 | 1 | 0%
1 | 2022-10-22 | 2 | 2022-10-23 | 2 | 2 | Released | 2022-10-23 | Creacion y configuracion cuenta Devops (SrumBoard y tareas) | 1 | 0%
Unplanned
Unplanned
Historias no asignadas |  |  |  | 0
Total Size |  |  |  | 12 | 12
|  |  |  | Estimadas | Reales
Formulas:
Start = IF(OR(B17="",[Incr.]=""),"",B17)
Start = IF(AND([Start, row above]<>"",[Days, row above]<>"",[Days]<>""),[Start, row above]+[Days, row above],"")
End = IF(OR([Start]="",[Days]=""),"",[Start]+[Days]-1)
End = IF(AND([Start]<>"",[Days]<>""),[Start]+[Days]-1,"")
Release Date = Tabla2[[#This Row],[End]]

## Product Backlog
Product Backlog
Story ID | Story name | Status | Size | Sprint | Priority | Story Type | Comments | Additional Comments
1 | Construccion Incial de MockUps | Done | 1 | 0 | 2 | Documentacion | Diseño mockups
2 | Construccion UML casos de uso | Done | 1 | 0 | 2 | Documentacion | Desarrollo inicial UML casos de uso de la aplicación
3 | Documento IEEE 29148 | Done | 1 | 0 | 2 | Documentacion | Llenado preliminar
4 | Desarrollar Product Backlook Priorizado | Done | 2 | 1 | 1 | Documentacion | Se Desarrolla Product Backlog Priorizado
5 | Construir Repositorio (Github) donde integraran el Trabajo | Done | 1 | 1 | 1 | Documentacion | Se Construye Repositorio (Github) en Proyecto de Equipo, El Proyecto tiene tres fases (To Do, In Progress, Done)
6 | Construir Archivo Gestion Configuracion | Done | 2 | 1 | 1 | Documentacion | Stack: MEVN Front: Vue Back: JavaScript, Express, Node BD: Mongo
7 | Construir Historias de Usuario a desarrollar en Sprint No.1 | Done | 5 | 1 | 1 | Documentacion | Construccion Historias de Usuario Spring 1
8 | Creacion y configuracion cuenta Devops (SrumBoard y tareas) | Done | 2 | 1 | 1 | Documentacion | Configuración inicial DevOps
Proyecto
Académica
Académica
Note on C2: ====== ID#AAAAO20iw4E Use the following statuses (2021-09-03 00:19:36) Planned (or empty) Ongoing Done Removed The sheet uses the above statuses in the formatting and calculation formulas.
Note on D2: ====== ID#AAAAO20iw4I Petri Heiramo (2021-09-03 00:19:36) Story Points or Ideal Days
Note on E2: ====== ID#AAAAO20iw4A Petri Heiramo (2021-09-03 00:19:36) Create a release plan by assigning stories to planned sprints. If there are more stories in the backlog than in the plan, leave the remaining stories unassigned to sprints.
Note on F2: ====== ID#AAAAO20iw38 Petri Heiramo (2021-09-03 00:19:36) You may assign priorities to the stories, but keep in mind that priority does not always equal implementation order.